Heruni Dict — v2

From letter dictionary to rich ancient-word dictionary

Digishot · Product & Engineering Brief · v2 Upgrade Plan

# 1. Where We Are and Where We're Going

## 1.1 v1 status (shipped)

v1 ships a functional letter dictionary: the 162 SSB root entries (39 single letters + 86 two-letter + 37 three-letter combinations) from Heruni's Appendix 10, browsable and searchable in Armenian and English. That is the spine. It works.

What v1 does not yet do is the thing that makes the product actually interesting: it doesn't deliver rich word entries. A user who looks up իշխանություն or հայրենիք today gets very little — the dictionary knows the letters but not the words built from them.

## 1.2 v2 goal

v2 turns Heruni Dict into a proper ancient-word dictionary. Every published word entry will carry five things: (1) the Heruni decomposition with tappable root pills, (2) a Heruni-style reconstructed meaning that reads like Heruni himself wrote it, (3) side-by-side classical etymology from Աճառյան and mainstream sources, (4) historical usage — when the word appears, in which texts, in which period, (5) related and derived words.

Launch target: 1,000 curated, high-quality entries — a focused corpus, not a machine-generated flood.

## 1.3 The three tracks of work

- Content enrichment — extend the data model so a word is no longer just (decomposition, meaning) but a full editorial record with etymology, attestations, usage, and references. Migrate v1 data; hand-edit the first wave.

- Knowledge ingestion — the Heruni book (321 pages) contains hundreds of specific word analyses beyond Chapter 2. Systematically extract them and make them first-class citations in entries.

- AI inference — Heruni-style — the unlock. Extract the rhetorical patterns Heruni uses to phrase his reconstructions (from his ~80 worked examples), then use Claude API to draft new reconstructions that follow those patterns faithfully — not letter-concatenation, but Heruni-voiced prose. Editor reviews every AI draft before publish.

# 2. Product Decisions (Locked)

| Decision | Resolution |
| --- | --- |
| AI inference approach | Pattern-driven. First we study Heruni's ~80 existing reconstructions, distill the rhetorical templates (possessive-owner, descended-from, elevated-status, state-holder, action-agent, etc.), then Claude API composes new reconstructions by (a) picking the right template, (b) filling it with SSB letter meanings, (c) producing Heruni-voiced Armenian + English prose. This is the methodological hinge — see §4. |
| Classical etymology placement | Side-by-side, equal weight. Two columns: 'Heruni method' and 'Classical etymology (Աճառյան et al.)'. The user sees both and can compare. No editorial hierarchy implied. |
| v2 content target | 1,000 curated words. All human-reviewed before publish. AI drafts are tools for editors, never public drafts. |
| AI generation model | Both: AI drafts at submission time (fast for users), cached in DB after editor approval, and on-demand generation for queries on words not yet seen. |
| Sources for classical etymology | Primary: Հր. Աճառյան, Հայերեն արմատական բառարան (HAB). Secondary: Նոր հայկազեան բառարան (NHB). For each sourced claim, the editor pastes the Աճառյան entry reference (volume + page). |

# 3. Data Model Changes

The v1 roots table stays as-is. The v1 words table expands significantly, and three new tables appear: patterns, sources, and ai_drafts.

## 3.1 words — expanded (v2)

Existing columns keep their shape. New columns added by migration — all nullable, filled in over time during editorial work.

| New column | Type | Notes |
| --- | --- | --- |
| classical_etymology_hy | text | Armenian prose describing Աճառյան / classical view |
| classical_etymology_en | text | English translation of the above |
| classical_source_ref | text[] | citations: ["Աճառյան HAB vol.II p.243", "NHB vol.I p.857"] |
| first_attestation | text | earliest known textual occurrence: "5th c., Ագաթանգեղոս" |
| usage_period | text | enum-ish: grabar ¦ middle-armenian ¦ ashkharhabar ¦ modern ¦ pan-historic |
| historical_usage_hy / _en | text | editorial prose: in which texts, how used, semantic evolution |
| cultural_notes_hy / _en | text | optional — mythological, religious, political context |
| related_word_ids | int[] | FKs into words table: same-root and derived words |
| heruni_book_refs | int[] | FKs into sources table — book pages that mention this word |
| pattern_id | int FK | which rhetorical pattern the reconstruction follows (see §3.3) |
| ai_draft_id | int FK | link to ai_drafts row the editor approved, for audit trail |

## 3.2 sources — Heruni book citations

Every page of the book that analyzes a specific word becomes a row here. Editors link word entries to sources instead of retyping citations.

- id · serial PK

- book_page · smallint — 1 to 321

- chapter · text — e.g. "2.7", "3.1"

- excerpt_hy · text — the exact passage quoted

- excerpt_en · text — editor translation

- mentioned_words · text[] — words analyzed on this page, for indexing

- image_url · text — optional scan of the page for verification

## 3.3 patterns — Heruni's rhetorical templates

This is where the AI inference work lives. Each pattern is a reusable template extracted from Heruni's ~80 worked examples. Editors define them; the AI uses them.

| Column | Type | Notes |
| --- | --- | --- |
| id | serial PK |  |
| code | text | short identifier: "possessive_owner", "descended_from", "elevated_status" |
| name_hy / name_en | text | human-readable labels |
| template_hy | text | templated Armenian phrase with slots: "{ADJ} {NOUN}-ի տեր" |
| template_en | text | "owner of the {ADJ} {NOUN}" |
| example_words | int[] | FKs into words that instantiate this pattern — reference set |
| applies_when | jsonb | triggering conditions: grammatical shape, category, suffix |

Example patterns distilled from the book (starter set — editors will grow this to ~20):

- possessive_owner — "owner of the {modified} {noun}". Fits: ասպետ (թամբած, զինված ձիու տեր), հովիվ (ոչխարի տեր).

- descended_from — "one born / descended from {source}". Fits: մարդ (ԱՐ-ից ծնվածը), Արա (ԱՐ-ի տված կյանք).

- elevated_status — "the {adjective} person/thing". Fits: հայր (բարձր մարդ), իշխան (շատերից բարձր).

- state_holder — "the state/condition of being {X}". Fits -ություն abstract nouns. իշխանություն, ազատություն, բարություն.

- action_agent — "the one who {verbs}". Fits: արարիչ (ստեղծող), սերմնացան (ցանող).

- place_of — "place where {X} happens/lives". Fits: հայրենիք (հայրերի տեղը), դպրոց.

- descriptive_compound — two roots literally stacked. Fits: արևելք (ԱՐ-ի ելք), մայրաքաղաք (գլխավոր քաղաք).

## 3.4 ai_drafts — audit trail for AI-generated content

Every time the AI generates a reconstruction, we save the prompt, the response, which patterns it chose, and which editor approved/rejected it. Essential for (a) editorial accountability, (b) fine-tuning the prompts over time, (c) never publishing something no human reviewed.

- id, word_id, pattern_id, created_at

- prompt_used · text — the full prompt sent to Claude

- model · text — "claude-opus-4-7" etc.

- raw_response · text — unmodified Claude output

- draft_meaning_hy / _en · text — parsed reconstruction

- reviewed_by · FK editors.id, nullable

- review_status · enum: pending | approved | edited | rejected

- final_meaning_hy / _en · text — what editor actually published (may differ from draft)

# 4. The AI Inference Engine — Heart of v2

This is the unlock. Three phases: pattern extraction (manual, one-time), pattern-driven drafting (runtime, per-word), editor review (always).

## 4.1 Phase A — Pattern extraction (Sprint 1–2, manual editorial + dev work)

Editors go through Heruni's ~80 worked reconstructions in Chapter 2.7 (pp. 115–119) and beyond. For each, they classify the rhetorical shape. Over one editorial week, a catalogue of ~15–25 distinct patterns emerges. Each pattern gets:

- A code and name (Armenian and English)

- A template phrase with slot markers

- 3–5 example words from Heruni that instantiate it

- Applicability rules — when the AI should pick this pattern over another

Why this matters: without the pattern catalogue, Claude would generate plausible-but-flat letter-concatenations. With it, Claude produces reconstructions that read like Heruni wrote them — because they follow the same rhetorical shapes Heruni used.

## 4.2 Phase B — Pattern-driven drafting (the runtime flow)

When the system needs to draft a reconstruction for word X:

- Step 1 — decompose X into SSB roots (greedy longest-match already exists from v1).

- Step 2 — classify X: suffix shape (-ություն → abstract, -իչ → agent, -ար → masc-noun, etc.), grammatical guess, category hint.

- Step 3 — retrieve candidate patterns: 2–4 patterns whose applies_when conditions match X's classification.

- Step 4 — retrieve the SSB meanings for each root in X, with Heruni's exact Armenian glosses.

- Step 5 — call Claude API with a carefully constructed prompt that includes: (a) the decomposition, (b) the root meanings, (c) the candidate patterns with example words, (d) instructions to produce a reconstruction in Heruni's voice.

- Step 6 — parse the response; save to ai_drafts with status 'pending'.

- Step 7 — present to editor in admin UI; editor approves / edits / rejects.

## 4.3 Phase C — Prompt engineering

The Claude prompt is a first-class artifact, versioned in the repo. Rough shape:

You are a lexicographer producing reconstructions in the methodology of
Paris Heruni's SSB theory. Given an Armenian word, its decomposition into
Heruni-roots, and the semantic gloss of each root, produce a reconstructed
meaning in Heruni's voice.
Word: {word}
Decomposition: {decomposition}
Root meanings: {root_table}
Suffix (if any): {suffix}
Grammatical shape: {shape}
Category guess: {category}
Here are {n} reconstructions Heruni himself wrote, which follow the
rhetorical pattern "{pattern_name}":
{example_reconstructions}
Now produce a reconstruction for {word} following the same rhetorical
shape. Rules:
1. Do not concatenate letter meanings literally. Synthesise.
2. Use Armenian prose that matches Heruni's register — formal but plain.
3. Produce Armenian and English in parallel.
4. If none of the given patterns fit, say so and propose a new one.
5. Cite which pattern you followed.
Output JSON: { "pattern_code": ..., "meaning_hy": ..., "meaning_en": ...,
"confidence": 1-5, "editor_notes": ... }

## 4.4 What this is NOT

- Not automatic publishing. Every AI draft is a draft. Editors ratify.

- Not a replacement for editorial judgment. The AI narrows the cognitive distance; the editor still decides.

- Not a claim that Heruni's methodology is correct etymology. The app presents it as Heruni's method — a methodology the user can explore, alongside mainstream etymology.

# 5. Sprint Plan — Six Sprints, Twelve Weeks

Assumes one full-stack developer + one editor working in parallel (editor full-time from Sprint 2 onwards). Add a second developer and Sprints 3–5 can compress by ~30%.

## Sprint 1 — Data model migration & pattern extraction kickoff (Weeks 1–2)

Developer goal: Migrate v1 schema to v2 without downtime, ship the expanded words table, stand up the sources and patterns tables, ship the admin UI for patterns.

Editor goal: Begin reading Chapter 2.7 line by line, tagging each of Heruni's ~80 worked reconstructions with a provisional pattern code. Output: spreadsheet with word → pattern assignments.

| # | Task | Acceptance Criteria | Pts |
| --- | --- | --- | --- |
| 1.1 | Migration: add all new columns to words (classical_etymology_hy/en, classical_source_ref, first_attestation, usage_period, historical_usage_hy/en, cultural_notes_hy/en, related_word_ids, heruni_book_refs, pattern_id, ai_draft_id). All nullable. Backfill nulls on existing v1 rows. | Migration runs on production DB with zero downtime. All v1 word pages still render. | 3 |
| 1.2 | New tables: sources, patterns, ai_drafts. With indexes (sources.book_page, patterns.code, ai_drafts.word_id). | Schema migrations apply and reverse cleanly; Prisma client regenerated. | 3 |
| 1.3 | Admin CRUD for patterns table. List view, edit form with Armenian/English template fields, example-words picker. | Editor can create a pattern, attach 3 example words, save, reload, see it listed. | 5 |
| 1.4 | Admin CRUD for sources table. Bulk import from a CSV the editor prepares (book_page, chapter, excerpt_hy, mentioned_words). | 200+ source rows uploaded via one CSV upload; linked to 50+ existing words via heruni_book_refs. | 5 |
| 1.5 | Expand admin word-edit form with all the new fields. Sections collapsed by default; expand on click. Markdown support for historical_usage and cultural_notes. | Editor can fill all new fields for one word, save, and see them render in the new UI (Sprint 2). | 3 |
| 1.6 | Data entry helper: on the word edit page, a sidebar showing (a) this word's current decomposition, (b) any sources rows whose mentioned_words array contains this word — suggested to link. | Editing իշխան shows any book page that mentions իշխան as a one-click link suggestion. | 3 |

## Sprint 2 — Rich word page UI & pattern catalogue (Weeks 3–4)

Developer goal: Ship the new word detail page — the mockup shared previously. Side-by-side Heruni method / classical etymology. Related words. Book references.

Editor goal: Finish pattern extraction — 15–25 patterns entered in the admin CMS, each with 3–5 example words. This is the raw material for the AI engine in Sprint 3.

| # | Task | Acceptance Criteria | Pts |
| --- | --- | --- | --- |
| 2.1 | New word detail page template at /{locale}/words/{slug}. Five sections: header, Heruni decomposition (pills), Heruni reconstruction (prose), classical etymology (side-by-side equal weight), historical usage + cultural notes (collapsibles), related words. | Visual matches design mockup. Lighthouse SEO ≥ 95. Page renders under 400ms server-side. | 8 |
| 2.2 | Classical etymology renderer: parallel two-column layout on desktop, stacked on mobile. Each column shows source citations as footnotes. | On mobile, Heruni column appears first, classical second, with clear visual separation. | 3 |
| 2.3 | Related words component: shows the 6–8 related_word_ids as card links with a one-line preview of each related word's decomposition. | Clicking a related word navigates; back button returns to original word. | 2 |
| 2.4 | Book references section: shows heruni_book_refs as clickable pill cards, each expanding to reveal the source excerpt. | Clicking a book-page reference expands inline without navigation. | 3 |
| 2.5 | Migrate the ~80 v1 words that were from the book itself: fill their pattern_id based on editor's Sprint 1 tagging, link them to sources rows, add placeholder classical_etymology fields for the editor to fill. | All 80 book-sourced words have pattern_id set and at least one heruni_book_refs link. | 3 |
| 2.6 | Pattern browse page /{locale}/patterns: lists all patterns with example words; clicking a pattern shows all words using it. | /hy/patterns/possessive_owner shows ասպետ, հովիվ, etc. | 3 |

## Sprint 3 — AI inference engine (Weeks 5–6)

Developer goal: Build the pipeline that takes an Armenian word and produces a Heruni-voiced draft reconstruction, cached, reviewable.

Editor goal: Curate and publish the first 300 of the 1,000 target words. For each, either ratify the AI draft, edit it, or reject and write one from scratch.

| # | Task | Acceptance Criteria | Pts |
| --- | --- | --- | --- |
| 3.1 | Word classifier module: given an Armenian word, returns {suffix, shape_guess, category_guess}. Heuristic rules on suffixes (-ություն, -իչ, -ական, -արան, -անոց), prefixes (ան-, ապ-), length, capitalization. | Classifier returns correct shape for 90% of a 100-word test set hand-labelled by editor. | 5 |
| 3.2 | Pattern retriever: given a classification, returns 2–4 candidate patterns ranked by fit. Uses patterns.applies_when jsonb rules + fallback to frequency. | For իշխանություն, state_holder pattern ranks first. | 3 |
| 3.3 | Prompt builder: assembles the full Claude prompt from word + decomposition + root meanings + candidate patterns + their example reconstructions. Prompts stored as templates in /prompts, versioned in git. | One-liner function buildPrompt(wordId) returns a complete, valid prompt string ≤ 4000 tokens. | 5 |
| 3.4 | Claude API integration: POST to Anthropic API with the built prompt, parse JSON response, save to ai_drafts with status='pending'. Error handling: retries on 5xx, fallback on JSON parse failure. | Running the pipeline on 20 test words produces 20 valid ai_drafts rows. | 5 |
| 3.5 | Admin review queue /admin/ai-drafts: paginated list of pending drafts. Each row shows word + draft reconstruction + pattern used + 'Approve' / 'Edit' / 'Reject' buttons. On approve, copies draft_meaning to words.meaning and sets words.ai_draft_id. | Editor can clear a queue of 20 drafts in under 15 minutes. | 5 |
| 3.6 | Bulk generate: admin action 'Generate drafts for next 100 words' — takes a curated list of target words, runs the pipeline, queues them for review. Shows progress. | 100 drafts generated and queued in under 10 minutes; editor sees progress bar. | 3 |

Cost planning: At ~2000 tokens per reconstruction (prompt + response), 1000 words ≈ 2M tokens. On Claude Opus ~$40–60 for the full launch corpus; on Sonnet a fraction of that. Budget $100 of API spend for v2 with generous retry margin. Cache results in ai_drafts so re-generation is opt-in.

## Sprint 4 — Content push to 600 words, classical etymology pipeline (Weeks 7–8)

Developer goal: Tooling to accelerate editorial content production. Second AI pipeline for classical etymology drafts.

Editor goal: Reach 600 published words by end of sprint. Focus on high-value categories: governance terms, kinship, astronomy, toponyms, theonyms.

| # | Task | Acceptance Criteria | Pts |
| --- | --- | --- | --- |
| 4.1 | Classical etymology AI draft pipeline: similar shape to 3.3–3.4 but prompts Claude to produce Aճառյան-style classical etymology given the word. Results go into words.classical_etymology_hy/en as pending, editor reviews. | Pipeline produces classical-etymology drafts for 100 words in under 15 minutes. Editor reviews them in /admin/classical-drafts. | 5 |
| 4.2 | Curated word list feature: admin can create named lists ("Governance terms", "Kinship", "Armenian toponyms") and bulk-queue them for AI drafting. Lists stored in DB. | Editor creates a 50-word list, clicks 'Generate all', returns in 10 minutes to a full review queue. | 3 |
| 4.3 | Diff view for editor approvals: when an AI draft is edited (not rubber-stamped), show the editor's final version side-by-side with the AI draft, highlighting changes. Used to spot prompt-engineering improvements over time. | Diff view renders for the last 50 approved drafts. | 3 |
| 4.4 | Prompt iteration tooling: admin page listing 'most edited' drafts — where editor changed the most from AI output. Signal for prompt improvement. | /admin/prompt-health shows a ranked list, most-edited first. | 2 |
| 4.5 | Export pipeline: nightly export of all published words as JSON + CSV. Backup + future open-dataset release. | Dump file lands in S3 every night at 02:00. | 2 |
| 4.6 | Public RSS / JSON feed of newly-published words — for Zontik social channels to auto-post about them. | /feed.xml validates; Zontik Instagram automation posts a 'word of the day' from this feed. | 3 |

## Sprint 5 — Search, discovery, 1000-word push (Weeks 9–10)

Developer goal: The product becomes discoverable. Full-text search across all the new fields. Pattern-based exploration. Daily word feature.

Editor goal: Reach 1000 published words. Final editorial pass on classical etymologies.

| # | Task | Acceptance Criteria | Pts |
| --- | --- | --- | --- |
| 5.1 | Full-text search v2: pg_trgm indexes across words.word_hy, transliteration, meaning_hy, meaning_en, classical_etymology_hy/en, historical_usage_hy/en. Ranked results with snippet highlighting. | Searching 'իշխ' returns իշխանություն, իշխան, իշխել ranked; searching 'Iranian' surfaces words with that etymology. | 5 |
| 5.2 | Faceted browse: filter words by category, period (grabar/middle/ashkharhabar/modern), pattern, has-classical-etymology, confidence. | User selects 'grabar' + 'possessive_owner' → gets ~15 words; URL shareable. | 3 |
| 5.3 | Word of the day: simple deterministic rotation through published words; featured on homepage with full entry preview. Shareable link. | Homepage shows a different word each day; og:image generated for sharing. | 3 |
| 5.4 | Word comparison view: user selects 2–3 words, sees a side-by-side of their decompositions, meanings, classical etymologies. Shareable. | URL /compare?words=մարդ,կին,հայր renders a three-column comparison. | 3 |
| 5.5 | Random word + 'explore this letter' navigation patterns for serendipity. | Homepage 'Random word' button navigates to a published word uniformly at random. | 2 |
| 5.6 | Structured data (schema.org DefinedTerm) for every word page. Better SEO, possible Google Knowledge Graph pickup. | JSON-LD validates in Google's Rich Results Test. | 2 |

## Sprint 6 — Polish, performance, launch (Weeks 11–12)

Developer goal: Production-grade: caching, observability, accessibility, legal. Ship v2.

Editor goal: Final content QA. Handbook updated. Soft-launch feedback incorporated.

| # | Task | Acceptance Criteria | Pts |
| --- | --- | --- | --- |
| 6.1 | Redis caching for hot word pages and root detail pages. TTL 15 min; invalidate on editor save. | Homepage TTFB < 150ms cached, < 500ms cold. Cache hit rate > 80% after 24h traffic. | 3 |
| 6.2 | Observability: Sentry for errors, structured logs, basic uptime monitoring. | Forced error in staging shows up in Sentry within 60s with stack trace. | 2 |
| 6.3 | Accessibility audit pass 2: all new v2 components keyboard-navigable, screen-reader labelled in both locales, focus visible. | axe-core reports zero critical on all v2 pages. | 3 |
| 6.4 | Methodology page /{locale}/about/methodology: explains Heruni's approach honestly, names it as his methodology, links to the book. Also explains how AI drafts work and that editors review. | Page live, linked from every word page footer with 'How do we derive meanings?'. | 3 |
| 6.5 | Credits and legal: book citation with author acknowledgement, AI disclosure in privacy policy, update terms for v2 features. | Legal pages updated; AI disclosure passes internal review. | 2 |
| 6.6 | Launch playbook: press list, Armenian linguistic community contacts, social announcement content. Coordinated with Zontik.am feature. | Launch day: Digishot blog post live, Instagram carousel posted, 10 linguist contacts notified personally. | 3 |
| 6.7 | Post-launch monitoring for first 72h: error rates, API costs, search queries that returned zero results (content gaps). | Dashboard live showing these metrics in real time. | 2 |

# 6. Risks & Mitigations

| Risk | Likelihood × Impact | Mitigation |
| --- | --- | --- |
| AI drafts read mechanically, not like Heruni | Medium × High | Pattern catalogue is the defense. Spend Sprint 2 editor-time to build ≥15 patterns with clean examples. Iterate prompts in Sprint 4 based on edit diffs. |
| Academic pushback from linguists who view Heruni's method as non-standard | High × Medium | Methodology page (6.4) is explicit: this is Heruni's method, not settled etymology. Side-by-side classical etymology neutralises the 'replacing scholarship' critique. |
| Editor throughput too slow for 1000 words in 12 weeks | High × High | At ~15 min per AI-drafted word reviewed (not written from scratch), 1000 words = 250 hours ≈ 6 weeks of one full-time editor. Plan has 10 weeks of editorial runway. Hire a second part-time editor if behind by week 6. |
| Copyright on book excerpts | Medium × High | Reach out to Heruni family / publisher Sprint 1. Limit excerpt length; paraphrase where possible; cite properly. Budget for licensing if required. |
| API costs exceed budget | Low × Low | Cache aggressively in ai_drafts. Use Sonnet for first pass, Opus only for tricky reconstructions. Monitor cost-per-word daily. |
| v2 launch overshadows existing letter dictionary value | Low × Low | Keep /roots navigation prominent; feature letters as entry points to words. |

# 7. Open Questions for the Team

- Editor staffing — is the current editor available full-time for the next 12 weeks, or do we need to hire a second? (This is the single biggest scheduling risk.)

- Initial curated word list — do we want to launch with a thematic emphasis (governance, cosmology, kinship, toponyms) or a balanced sample? A thematic v2 gives a stronger press angle; a balanced v2 feels more like a dictionary.

- Aճառյան licensing — Հայերեն արմատական բառարան is public-domain in Armenia (author died 1953). We can quote directly. Confirm before publishing citations.

- AI transparency — how explicit should the 'AI-assisted draft, editor-reviewed' label be on each word page? Recommended: small footer icon + link to methodology page. Alternative: no label (just attribute to the editor who approved).

- Pattern catalogue curation — should the pattern list be public, as its own browsable section? Recommended yes — it's a compelling window into Heruni's methodology.

- International English — do we target Diaspora Armenian English readers specifically, or general English audience? Affects tone of English reconstructions.